## Innovation Model
Assumptions |  |  | Year
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
R&D |  |  | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
Maintenance | 13% |  | 0 | 130000 | 243100 | 341497 | 427102.39 | 501579.0793 | 566373.799 | 622745.2051 | 671788.3285
Sustainment | 13% |  | 0 | 130000 | 243100 | 341497 | 427102.39 | 498420.9207 | 433626.201 | 377254.7949 | 328211.6715
Innovation |  |  | 1000000 | 740000 | 513800 | 317006 | 145795.22 | 0 | 0 | 0 | 0
Accumulated asset |  | 0 | 1000000 | 1870000 | 2626900 | 3285403 | 3858300.61 | 4356721.5307 | 4790347.7317 | 5167602.5266 | 5495814.1981

## Estimating Model
Development Estimate Model |  |  |  |  | J Exponents for Jones's first-order estimate
Factor | Units | Formula | Example Project | Your Project | Kind of software | Best in class | Average | Worst in class
Tuning Factor | dim | J | 0.4 | 0.4 | Systems | 0.43 | 0.45 | 0.48
Lines of Code | LOC | LOC | 75000 | 75000 | Business | 0.41 | 0.43 | 0.46
LOC/FP | LOC/FP | LOC-per-FP | 54 | 54 | Shrink-wrap | 0.39 | 0.42 | 0.45
Function Points | FP | FP | 1388.8889 | 1388.8889
Estimated project duration | months | FPJ | 18.0745 | 18.0745
Development resources | persons | FP2*J/27 | 12.0996 | 12.0996
Total development effort | person-months | FP3*J/27 | 218.6942 | 218.6942
Average productivity | LOC/person-month | 27*FP^(1-3*J) | 342.9446 | 342.9446
LOC | Duration (months) | Resources (persons) | Total Effort (person-months) | Productivity (LOC/person-month)
10000 | 8.0731 | 2.4139 | 19.4878 | 513.1405
20000 | 10.6526 | 4.2029 | 44.7713 | 446.7147
30000 | 12.5283 | 5.8132 | 72.8298 | 411.9192
40000 | 14.0562 | 7.3176 | 102.8574 | 388.8878
50000 | 15.3685 | 8.7478 | 134.4398 | 371.9138
60000 | 16.5311 | 10.1214 | 167.319 | 358.5965
70000 | 17.5825 | 11.4498 | 201.3174 | 347.7096
75000 | 18.0745 | 12.0996 | 218.6942 | 342.9446
80000 | 18.5472 | 12.7407 | 236.3043 | 338.5465
90000 | 19.4419 | 13.9996 | 272.1791 | 330.6647
100000 | 20.2788 | 15.2307 | 308.8615 | 323.7698

## Tracking Model
Assumptions
LOC/FP |  | 54
$K/manyear |  | 80
J Tuning Factor |  | 0.4
Scope |  | 75000
Ideal team size |  | 5
person-day/month |  | 15
Period | Scope |  |  | Estimates | [5 empty] | Costs |  | Measured |  |  | Metrics
| Original Estimated Scope | Scope Creep | Estimated Scope including Creep | Project Duration | Required Project Resources | Estimated Productivity | Estimated lines-of-code produced in period | Accumulated lines-of-code | Remaining scope | Accum Cost | Cost/LOC | Actual Project Resources | Actual (Measured) LOC | Measured remaining scope | Agile Productivity Ratio | Allowable scope change
Month | Lines of Code | Percent per Month | Lines of Code | Months | Persons | Lines-of-Code/Person-Month | Lines of Code | Lines of Code | Lines of Code | $ | $/LOC | FTE Persons | Lines of Code | Lines of Code | % | Percent per Month
1 | 75000 | 0% | 75000 | 18.0745 | 12.0996 | 452.274 | 1809.0958 | 1809.0958 | 73190.9042 | 26666.6667 | 14.7403 | 4 | 0 | 75000 | 105.7% | 5.533%
2 |  | 1.95% | 75000 | 18.0745 | 12.0996 | 452.274 | 1809.0958 | 3618.1917 | 71381.8083 | 53333.3333 | 14.7403 | 4 |  |  | 105.7% | 5.533%
3 |  | 1.95% | 76462.5 | 18.2147 | 12.288 | 408.6757 | 2452.0539 | 6070.2456 | 70392.2544 | 93333.3333 | 15.3755 | 6 |  |  | 95.54% | 5.49%
4 |  | 1.95% | 77953.5188 | 18.3559 | 12.4793 | 408.6757 | 2452.0539 | 8522.2996 | 69431.2192 | 133333.3333 | 15.6452 | 6 |  |  | 95.54% | 5.448%
5 |  | 1.95% | 79473.6124 | 18.4983 | 12.6736 | 408.6757 | 2452.0539 | 10974.3535 | 68499.2588 | 173333.3333 | 15.7944 | 6 |  |  | 95.54% | 5.406%
6 |  | 1.95% | 81023.3478 | 18.6417 | 12.8709 | 408.6757 | 2452.0539 | 13426.4075 | 67596.9403 | 213333.3333 | 15.8891 | 6 |  |  | 95.54% | 5.364%
7 |  | 1.95% | 82603.3031 | 18.7863 | 13.0713 | 408.6757 | 2452.0539 | 15878.4614 | 66724.8417 | 253333.3333 | 15.9545 | 6 |  |  | 95.54% | 5.323%
8 |  | 1.95% | 84214.0675 | 18.932 | 13.2748 | 408.6757 | 2452.0539 | 18330.5154 | 65883.5521 | 293333.3333 | 16.0025 | 6 |  |  | 95.54% | 5.282%
9 |  | 1.95% | 85856.2418 | 19.0788 | 13.4815 | 408.6757 | 2452.0539 | 20782.5693 | 65073.6725 | 333333.3333 | 16.0391 | 6 |  |  | 95.54% | 5.241%
10 |  | 1.95% | 87530.4385 | 19.2268 | 13.6914 | 408.6757 | 2452.0539 | 23234.6233 | 64295.8153 | 373333.3333 | 16.068 | 6 |  |  | 95.54% | 5.201%
11 |  | 1.95% | 89237.2821 | 19.3759 | 13.9046 | 408.6757 | 2452.0539 | 25686.6772 | 63550.6049 | 413333.3333 | 16.0914 | 6 | 18151 | 71086.2821 | 95.54% | 5.161%
12 |  | 1.95% | 90977.4091 | 19.5261 | 14.1211 | 408.6757 | 2452.0539 | 28138.7312 | 62838.6779 | 453333.3333 | 16.1107 | 6 |  |  | 95.54% | 5.121%
13 |  | 1.95% | 92751.4686 | 19.6775 | 14.3409 | 343.6539 | 4123.8467 | 32262.5779 | 60488.8907 | 533333.3333 | 16.531 | 12 |  |  | 80.34% | 5.082%
14 |  | 1.95% | 94560.1222 | 19.8301 | 14.5642 | 343.6539 | 4123.8467 | 36386.4247 | 58173.6975 | 613333.3333 | 16.8561 | 12 |  |  | 80.34% | 5.043%
15 |  | 1.95% | 96404.0446 | 19.9839 | 14.791 | 343.6539 | 4123.8467 | 40510.2714 | 55893.7732 | 693333.3333 | 17.115 | 12 |  |  | 80.34% | 5.004%
16 |  | 1.95% | 98283.9234 | 20.1389 | 15.0213 | 325.0078 | 4875.1168 | 45385.3882 | 52898.5352 | 793333.3333 | 17.4799 | 15 |  |  | 75.98% | 4.966%
17 |  | 1.95% | 100200.46 | 20.2951 | 15.2552 | 325.0078 | 4875.1168 | 50260.5051 | 49939.9549 | 893333.3333 | 17.7741 | 15 |  |  | 75.98% | 4.927%
18 |  | 1.95% | 102154.3689 | 20.4524 | 15.4927 | 330.6622 | 4629.271 | 54889.7761 | 47264.5928 | 986666.6667 | 17.9754 | 14 |  |  | 77.31% | 4.889%
19 |  | 1.95% | 104146.3791 | 20.6111 | 15.7339 | 330.6622 | 4629.271 | 59519.0471 | 44627.332 | 1080000 | 18.1455 | 14 |  |  | 77.31% | 4.852%
20 |  | 1.95% | 106177.2335 | 20.7709 | 15.9789 | 319.806 | 5116.8958 | 64635.9429 | 41541.2906 | 1186666.6667 | 18.3592 | 16 |  |  | 74.77% | 4.814%
21 |  | 1.95% | 108247.6896 | 20.932 | 16.2277 | 319.806 | 5116.8958 | 69752.8387 | 38494.8509 | 1293333.3333 | 18.5417 | 16 |  |  | 74.77% | 4.777%
22 |  | 1.95% | 110358.5195 | 21.0943 | 16.4803 | 319.806 | 5116.8958 | 74869.7344 | 35488.7851 | 1400000 | 18.6991 | 16 |  |  | 74.77% | 4.741%
23 |  | 1.95% | 112510.5106 | 21.2579 | 16.7369 | 325.0078 | 4875.1168 | 79744.8513 | 32765.6594 | 1500000 | 18.81 | 15 |  |  | 75.98% | 4.704%
24 |  | 1.95% | 114704.4656 | 21.4227 | 16.9975 | 325.0078 | 4875.1168 | 84619.9681 | 30084.4975 | 1600000 | 18.9081 | 15 |  |  | 75.98% | 4.668%
25 |  | 1.95% | 116941.2027 | 21.5889 | 17.2622 | 302.4538 | 6049.0765 | 90669.0446 | 26272.1581 | 1733333.3333 | 19.1171 | 20 |  |  | 70.71% | 4.632%
26 |  | 1.95% | 119221.5561 | 21.7563 | 17.5309 | 302.4538 | 6049.0765 | 96718.1212 | 22503.435 | 1866666.6667 | 19.3001 | 20 |  |  | 70.71% | 4.596%
27 |  | 1.95% | 121546.3765 | 21.925 | 17.8039 | 302.4538 | 6049.0765 | 102767.1977 | 18779.1788 | 2000000 | 19.4615 | 20 | 110061 | 11485.3765 | 70.71% | 4.561%
28 |  | 1.95% | 123916.5308 | 22.095 | 18.0811 | 302.4538 | 6049.0765 | 108816.2742 | 15100.2566 | 2133333.3333 | 19.6049 | 20 |  |  | 70.71% | 4.526%
29 |  | 1.95% | 126332.9032 | 22.2664 | 18.3626 | 280.5922 | 7575.9902 | 116392.2645 | 9940.6387 | 2313333.3333 | 19.8753 | 27 |  |  | 65.6% | 4.491%
30 |  | 1.95% | 128796.3948 | 22.439 | 18.6485 | 280.5922 | 7575.9902 | 123968.2547 | 4828.1401 | 2493333.3333 | 20.1127 | 27 |  |  | 65.6% | 4.457%
31 |  | 1.95% | 131307.9245 | 22.613 | 18.9389 | 280.5922 | 7575.9902 | 131544.2449 | -236.3205 | 2673333.3333 | 20.3227 | 27 | 137180 | -5872.0755 | 65.6% | 4.422%